## Intro
Sample Primary Prevention Program Plan -- Academic Year
(Addressing sexual assault, dating violence, domestic violence and stalking)
This sample primary prevention program plan aims to provide examples of how to think about, plan, and evaluate primary prevention programming and awareness campaigns on sexual assault, dating violence, domestic violence, and stalking for new and current students and employees, as required by the Clery Act.
The plan is broken up into tabs representing months of the academic year followed by an Evaluation tab. Each month tab contains suggested themes or areas of focus based on common happenings during that month or national awareness month endeavors already taking place. Additionally, each tab contains examples of sample programs that could take place aligning with the suggested themes/focuses. The example programs include a description (including sample learning objectives), type of program (PP = primary prevention or AC = awareness campaign), audience (student or employee) and frequency.
The evaluation tab contains all of the components that should be addressed at some point throughout the academic year through these primary prevention programs and awareness campaigns according to the VAWA Amendments to Clery. Please note: no one program needs to, or truly can, contain all of the evaluation elements. Use this tab to evaluate each program that occurs throughout the year according to what elements it contains. Two example evaluations of programs listed in this document are provided.

## AugSept
SUGGESTED THEMES/FOCUSES: New Student/Employee Orientation; Red Zone -- first six weeks of the school year, increased rate of sexual assaults
Program Name | Type | Description | Audience | Frequency
New Student Orientation | PP | Comprehensive overview of sexual misconduct policy, response procedures and community expectations. LO 1: Inform what is considered prohibited conduct. LO2: Define and explain the role of CSAs and REs and examples of each role. LO3: Explain reporting options, importance of preserving evidence, how to obtain accommodations. | Incoming new students or transfer students | Beginning of each semester
New Student Orientation Bystander Intervention Program | PP | Introducing bystander intervention philosophy on campus.LO 1: Definebystander intervention and what it can look like. LO2: Communicate various strategies one can use as a bystander. LO3: Share information on positive impact bystander intervention can have on campus community. | Incoming new students or transfer students | Beginning of each semester
New Employee Orientation | PP | Comprehensive overview of sexual misconduct policy, response procedures and community expectations. LO 1: Inform what is considered prohibited conduct. LO2: Explain reporting options, both what to do when students report to them and how to report themselves; review role of CSAs and REs and who they are within those two groups. LO3: Share information on importance of preserving evidence, how to obtain accommodations. LO4: Share bystander intervention tips, info on risk reduction. | New employees | Bi-monthly all year
New Employee Bystander Intervention Program | PP | Introducing bystander intervention philosophy on campus. LO 1: Defining bystander intervention and what it can look like. LO2: Communicate various strategies one can use as a bystander. LO3: Share information on positive impact bystander intervention can have on campus community. | New employees | Bi-monthly all year
Student Code of Conduct Awareness Campaign | AC | Passive program reiterating throughout the month the code of conduct, including the sexual misconduct policy and the disciplinary procedures for students following such an allegation. Flyers, digital workshops all students must take during September, email newsletters sent each week | All Students | Throughout month
Employee Handbook Awareness Campaign | AC | Passive program reiterating throughout the month employee behavior expectations, particularly the sexual misconduct policy. Flyers, digital workshops mandatory for all employees to take during September, email newsletters each week focusing on a different aspect of a policy, resolution procedures or sanctions. | All Employees | Throughout month

## October
SUGGESTED THEMES/FOCUSES: Domestic Violence Awareness Month; Alcohol Awareness Month (can tie in or co-program), Bystander Intervention Reboot (Culture around celebrating Halloween can involve costume parties or increased alcohol or drug use. This climate allows for increased opportunities to discuss community engagement and discussion on bystander intervention and participation in responsible/safe practices.)
Program Name | Type | Description | Audience | Frequency
Party with a Purpose | AC | Awareness campaign on safe drinking and partying tips including bystander intervention tips on what to do in prepping to go out and how to address problematic behavior in the moment--partnership with Residence Life for a passive program ---flyers in residence halls and on bulletin boards, slides on TVs in academic centers and student union, tabling once a week during lunch hour in dining halls providing tip sheets. | All students | Throughout month
Domestic Violence/Dating Violence Happens | PP | Information session/Discussion series held weekly throughout the month with student organizations and leaders: RAs, Athletes, Greek Life, Student Government, Arts groups; Last week of month two sessions held that are open to entire campus community. LO 1: Discussing prevalence rates and signs of abuse. LO 2: Learn how to talk to friends and family when in such a situation. LO 3: Understand how to intervene helpfully as a friend when someone you know is the victim of such abuse. LO4: Review reporting options and response procedures. | All students | Weekly during month
Domestic Violence/Dating Violence Happens | PP | Information session/Discussion series for employees about prevalence of and signs/manifestations of such violence amongst adults. LO1: Share tips and techniques for addressing coworkers as a bystander intervening. LO2: Share methods preparing employees for receiving reports from students or confronting students when concerned. LO3: Review reporting options and response procedures.

## November
SUGGESTED THEMES/FOCUSES: Risk Reduction Reboot, Healthy Strategies for Returning to Environments that Might be Unsafe/Triggering, Reviewing Reporting Options
Program Name | Type | Description | Audience | Frequency
Reviewing Reporting Options | AC | Comprehensive passive programming campaign highlighting the various reporting options a victim of dating violence, domestic violence, sexual assault and stalking has on campus and within the local community; completed in collaboration with Health and Wellness, Counseling Center, Public Safety, Title IX office, Residence Life. | All--students and employees | Throughout the month
Redefining Risk Reduction | PP | Town Hall Meeting/Open Forum to solicit from campus community thoughts on the meaning of risk reduction and how that is communicated on campus paired with lecture/information on risk reduction redefined within the Clery Act -- why that was done as part of VAWA Amendments and what that means about how we use the term in violence prevention moving forward. LO1: Understand the definition of risk reduction in the Clery Act and how it differs from previous understanding. LO2: Catalog differing thoughts and feelings from community members about how institution communicates about risk reduction. LO3: Brainstorm areas of campus communication that could be edited to include revised definition of risk reduction. | All--students and employees | Once this month

## December
SUGGESTED THEMES/FOCUSES: Culturally relevant and inclusive self care reminders/tips/strategies
Program Name | Type | Description | Audience | Frequency
Celebrating You! | AC | Program highlighting and celebrating the various holiday celebrations and traditions that occur at this time of year and, simultaneously, sharing suggestions for how to best care for one's self/family/friends in conjunction with such celebrations. Passive program advertised mainly in the student center through flyers, bulletin boards, TV sliders, tabling. | All students | Ongoing throughout month

## January
SUGGESTED THEMES/FOCUSES: National Stalking Awareness Month
Program Name | Type | Description | Audience | Frequency
New Student Orientation | PP | Comprehensive overview of sexual misconduct policy, response procedures and community expectations. LO 1: Inform what is considered prohibited conduct. LO2: Define and explain the role of CSAs and REs and examples of each role. LO3: Explain reporting options, importance of preserving evidence, how to obtain accommodations. | Incoming students or transfer students | Beginning of each semester
New Student Orientation Bystander Intervention Program | PP | Introducing bystander intervention philosophy on campus. LO 1: Define bystander intervention and what it can look like. LO2: Communicate various strategies one can use as a bystander. LO3: Share information on positive impact bystander intervention can have on campus community. | Incoming new students or transfer students | Beginning of each semester
New Employee Orientation | PP | Comprehensive overview of sexual misconduct policy, response procedures and community expectations. LO 1: Inform what is considered prohibited conduct. LO2: Explain reporting options, both what to do when students report to them and how to report themselves; review role of CSAs and REs and who they are within those two groups. LO3: Explain the importance of preserving evidence, how to obtain accommodations. LO4: Share bystander intervention tips, info on risk reduction. | New employees | Bi-monthly all year
New Employee Bystander Intervention Program | PP | Introducing bystander intervention philosophy on campus. LO 1: Define bystander intervention and what it can look like. LO2: Communicate various strategies one can use as a bystander. LO3: Share information on positive impact bystander intervention can have on campus community. | New employees | Bi-monthly all year
Everything You Thought You Knew About Stalking | PP | In depth informational session explaining the insidiousness of stalking culture and how pervasive it is within the entertainment and education industries. LO1: Review signs of stalking behavior. LO2: Share bystander intervention tips and information on how to report both on campus and to local law enforcement. LO3: Explain various resources on campus for victims or survivors particularly focusing on accommodations one can receive even if not moving forward with a disciplinary process. | All Students | Once this month
Stalking Awareness Campaign | AC | Comprehensive awareness campaign about the signs that indicate someone is being stalked or behaviors that, if pervasive, are stalking. | All students and employees | Throughout month

## February
SUGGESTED THEMES/FOCUSES: Healthy Relationships
Program Name | Type | Description | Audience | Frequency
Healthy Communication within Relationships | PP | Program focusing on how healthy communication is the foundation of a strong relationship --whether family, friends or a romantic partner; provides culturally relevant skill building workshops in the form of "speed dating stations" to allow participants to practice different verbal and nonverbal communication strategies such as active listening, rephrasing, reflection and validation; shares information on "love languages". LO1: Understand value of healthy communication in general and how it is the foundation of healthy relationships, in particular. LO2: Learn what you value in communication. LO3: Practice new verbal communication strategies. LO4: Identify what love languages you prefer to receive and what love language you prefer to use to show love. | First year resident students/student athletes/Greek students; facilitated by senior students and leaders within each of these groups | Three separate sessions this month
Signs of Sexual Assault, Domestic Violence, Dating Violence and Stalking | AC | Flyer/tabling/passive programming campaign to remind folks of the warning signs indicating someone might be a victim/survivor and what to do to help oneself or a friend--options for reporting, collecting evidence, participating in the disciplinary process, receiving accommodations. Focuses on the impact of trauma and how that impacts recognition of being a victim as well as reporting. | All | Throughout month

## March
SUGGESTED THEMES/FOCUSES: Safer Spring Break; Mental Health Awareness
Program Name | Type | Description | Audience | Frequency
Safe Spring Break Tips and Strategies | AC | Program conducted in conjunction with Health and Wellness and Greek Life for all students traveling for spring break--reviews local, state, national and international laws and standards around drinking, drug use and reporting dating violence, domestic violence, sexual assault and stalking. | All students | Three times this month

## April
SUGGESTED THEMES/FOCUSES: Sexual Assault Awareness Month
Program Name | Type | Description | Audience | Frequency
Take Back the Night | AC/PP | Open forum for survivors to share their stories | All--students and employees | Once this month
Rape Culture is Real | PP | Interactive program highlighting and analyzing the underlying thoughts and assumptions grounding rape culture today and how to go about addressing them as a campus community. Co-sponsored by Health and Wellness; Women's Center and the Title IX Office. LO1: Define "rape culture". LO2: Identify elements of current campus life, including "traditions" that reinforce rape culture, incorporate campus climate survey--either launching one or reviewing results from latest. LO3: Establish awareness of what steps can be taken to address and confront rape culture both on an individual and systemic level. | All students and employees | Once this month

## Evalauting Each Program
Program Name | Research used to inform program or assessment method. List research informing program or evaluation tools for program. | Incorporates content on stopping violence before it occurs. Indicate yes or no. If yes, indicate how. | Promotes positive and healthy behaviors that foster healthy, mutually respectful relationships and sexuality. Indicate yes or no. If yes, indicate how. | Encourages safe bystander intervention. Indicate yes or no. If yes, indicate how. | Seeks to change behavior or social norms in healthy/safe directions. Indicate yes or no. If yes, indicate how. | Includes information on recognizing situations of potential harm. Indicate yes or no. If yes, indicate how. | Addresses institutional structures and cultural conditions that facilitate violence. Indicate yes or no. If yes, indicate how. | Gives strategies for overcoming barriers to intervening/ Decrease bystander inaction. Indicate yes or no. If yes, indicate how. | Identifies safe and effective intervention options. Indicate yes or no. If yes, indicate how. | Provides information to decrease perpetration. Indicate yes or no. If yes, indicate how. | Provides information that increases empowerment for victims. Indicate yes or no. If yes, indicate how. | Culturally relevant Indicate yes or no. If yes, indicate how. | Inclusive of diverse communities and identities (LGBTQ, students with disabilities, minority students, other students and employees). Indicate yes or no. If yes, indicate how. | Considers environmental risk and protective factors as they occur on the individual, relationship, institutional, community, and societal levels. Indicate yes or no. If yes, indicate how. | Acknowledges prohibition of sexual assault, domestic violence, dating violence, and stalking as defined by the Clery Act. Indicate yes or no. | Incorporates jurisdictional definitions for sexual assault, domestic violence, dating violence, and stalking. Indicate yes or no. If yes, indicate how. | Addresses procedures victims should follow in cases of sexual assault, domestic violence, dating violence, or stalking. Indicate yes or now. If yes, indicate how.
EX. New Student Orientation | Spring 2016 campus climate survey; pre and post assessments used for evaluation. | Yes--importance of bystander intervention but explantion that we will go more in depth in this area in the separate bystander intervention program. | Yes, coercion activity. | Yes but only high level--separate bystander intervention program focuses in depth on this. | Yes, addresses this campus' cultural norms around sexual assault and goals of what it wants to change. | No--part of another program. | Yes but only high level, more in depth throughout the year in other programming. | Only high level--more info in separate program. | No--part of another program. | Yes---addresses redefining risk reduction and bystander intervention at a high level. | Yes, reviews resources for reporting, receiving accommodations and the disciplinary process. | Yes--addresses how all individuals no matter race/nationality/sexual orientation/gender identity/gender can be victims or perpetrators of sexual assault--identifies how some resources are not everyone's resources---addresses barriers to certain resources (discomfort with the police for reporting or going to counseling for support for example.) | Yes--high level. | Yes--high level--go more in depth throughout year. | Yes | Yes | Yes
EX. Celebrating You! |  |  |  |  | Yes |  | Yes |  |  |  |  | Yes